## Summary E2E
MILESTONE LEVEL | ID | BASELINE FINISH | PROJECTED FINISH | END-TO-END B/W, Cerro Pachon - La Serena | END-TO-END B/W, La Serena - NCSA | Bandwidth Achieved through Demonstration
2 | DM-NET-1 | 2015-06-11 | 2015-06-11 | 0.5 Gbps | Max: 1G Best Effort | 0.5 Gbps (operational)
2, 3 | DM-NET-2, -3, 6, DMTC-6800-1310 | 2018-03-27 | 2018-06-30 | 2 x 100 (shared AURA DWDM) | Max: 20G Best Effort | 46Gbps (LSST First Light demo)
3 | DM-NET-4, DMTC-6800-1320 | 11/30/18, 7/3/19 | 2019-07-03 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) | Max: 20G Best Effort | 80Gbps (LSST SC18 demo)
3 | DM-NET-5 | 2019-07-03 | 2020-01-01 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) | Max: 40G Best Effort | 0
3 | DMTC-6800-1330 | 2020-07-06 | 2020-07-06 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) | Max: 140G Best Effort | 0
3 | DMTC-6800-1340 | 2021-07-02 | 2021-07-02 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) | Max Dedicated: 200G dedicated up to NCSA. 300G at NCSA. Burst: 100G | 0

## Detailed by Segment
MILESTONE LEVEL | ID | ACTIVITY | BASELINE FINISH | PROJECTED FINISH | END-TO-END B/W, Cerro Pachon - La Serena | Bandwidth Achieved through Demonstration | MTN - BASE | BASE LAN | END-TO-END B/W, La Serena - NCSA | BASE - SCL | SCL CONNECTIONS | SCL - MIA | SCL - SAO | SAO - MIA | SAO - BOCA | BOCA - MIA | MIA - JAX | JAX - ATL | BOCA - ATL | JAX - 600 W. CHI | ATL - 600 W. Chicago | ATL - 710 N. Lake CHI | 600 W. CHI - LDF | 710 N. Lake CHI - LDF | NPCF - LSST-Core
JK | JK | JK | JK | JK | JK | NET | RL | RL | JB | RL, SJ | SJ | JI | JI | JI | JI | JI | JI | JI | JI | JI |  |  |  |  | MK
2 | DM-NET-1 | Base - Archive Network Functional 1 Gbps | 2015-06-11 | 2015-06-11 | 0.5 Gbps | 0.5 Gbps (operational) | Microwave only, no path diversity | Pre-LSST, AURA LAN | Max: 1G Best Effort | AURA 1 x 1G (dedicated) (protected) | Pre-LSST, 2 x 10G (shared) | 1 x 10G (leased) (shared) | 1 x 10G (leased) (shared) | 2 x 10G, 1 x 100G, path diversity (leased) (shared) | None | None | 2 x 10G (MPLS pw) + 1 x 100G (alien wave) (shared) | None | None | 100G (AL2S) (shared) | None | None | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | 2x40G
2, 3 | DM-NET-2, -3, 6, DMTC-6800-1310 | Mountain - Base Network Functional 2 x 100 Gbps, Summit LAN Installed, Initial Network Ready (Summit), Network Acceptance/Verification Review for Early Integration | 2018-03-27 | 2018-06-30 | 2 x 100 (shared AURA DWDM) | 46Gbps (LSST First Light demo) | AURA DWDM, no path diversity | Pre-LSST, AURA LAN | Max: 20G Best Effort | LSST 10 x 10G (dedicated), 1 x 4 G (dedicated) | 1 x 100G (dedicated) (protected) | 1 x 10G + 1 x 100G (leased) (shared) | 1 x 100G (leased) (shared) | 2 x 10G, 1 x 100G, path diversity (leased) (shared) | None | None | 2 x 10G (MPLS pw) + 1 x 100G (alien wave) (shared) | None | None | 100G (AL2S) (shared) | None | None | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | 2x40G (can expand to additional 40G) (shared with DM)
3 | DM-NET-4, DMTC-6800-1320 | Base LAN installed, Network Acceptance/Verification Review for Full Integration | 11/30/18, 7/3/19 | 2019-07-03 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) | 80Gbps (LSST SC18 demo) | AURA DWDM, LSST DWDM, no path diversity | LSST LAN | Max: 20G Best Effort | LSST 10 x 10G (dedicated), AURA 4 x 10G (shared), backup 1 x 4 G (dedicated) | 1 x 100G (dedicated) (protected) | 1 x 100G (leased) (shared) | 1 x 100G (leased) (shared) + 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 1 x 100G (leased) (shared) + 2 x 100G (spectrum) (shared) via BOCA | 1 x 100G (spectrum) (dedicated) | 1 x 100G (spectrum) (shared) | 2 x 100G (alien wave) (shared) | None | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 100G (AL2S) (shared) | None | None | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | 2x40G (can expand to additional 40G) (shared with DM)
3 | DM-NET-5 | Base - Archive Network Functional 100 Gbps | 2019-07-03 | 2020-01-01 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) |  | AURA DWDM, LSST DWDM, no path diversity | LSST LAN | Max: 40G Best Effort | LSST 10 x 10G (dedicated), AURA 4 x 10G (shared), backup 1 x 4 G (dedicated) | 1 x 100G (dedicated) (protected) | 1 x 100G (leased) (shared) | 1 x 100G (leased) (shared) + 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 1 x 100G (leased) (shared) + 3 x 100G (spectrum) (shared) via BOCA | 1 x 100G (spectrum) (dedicated) | 1 x 100G (spectrum) (shared) | 2 x 100G (alien wave) (shared) | 1 x 100G (MPLS PW) (shared) | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 100G (AL2S) (shared) | 1 x 20G (MPLS PW) (Esnet) | 1 x 20G (MPLS PW) (Esnet) | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | Multiple 100G (shared with DM)
3 | DMTC-6800-1330 | Network Acceptance/Verification Review for Science Verification | 2020-07-06 | 2020-07-06 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) |  | AURA DWDM, LSST DWDM, no path diversity | LSST LAN | Max: 140G Best Effort | LSST 20 x 10G (dedicated), AURA 4 x 10G (shared), backup 1 x 4 G (dedicated) | 2 x 100G (dedicated) (protected) | 1 x 100G (leased) (shared) | 1 x 100G (leased) (shared) + 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 1 x 100G (leased) (shared) + 3 x 100G (spectrum) (shared) via BOCA | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 1 x 100G (spectrum) (shared) | 2 x 100G (alien wave) (shared) | 1 x 100G (MPLS PW) (shared) | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 100G (AL2S) (shared) | 1 x 20G (MPLS PW) (Esnet) | 1 x 20G (MPLS PW) (Esnet) | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | Multiple 100G (shared with DM)
3 | DMTC-6800-1340 | Network Acceptance/Verification Reviewfor Full Operations | 2021-07-02 | 2021-07-02 | 6 x 100 (dedicated LSST DWDM) + 2 x 100 (shared AURA DWDM) |  | AURA DWDM, LSST DWDM, no path diversity | LSST LAN | Max Dedicated: 200G dedicated up to NCSA. 300G at NCSA. Burst: 100G | LSST 20 x 10G (dedicated), AURA 4 x 10G (shared), backup 1 x 40G (dedicated) or 100 Gbps if possible, | 2 x 100G (dedicated) (protected). An alternative DC TBD as a secondary PoP | 1 x 100G (leased) (shared) | 1 x 100G (leased) (shared) + 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 1 x 100G (leased) (shared) + 4 x 100G (spectrum) (shared) via BOCA | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 2 x 100G (spectrum) (shared) | 2 x 100G (alien wave) (shared) + 1 x 100G (alien wave) (dedicated) | 1 x 100G (spectrum) (dedicated) | 1 x 100G (spectrum) (dedicated) + 1 x 100G (spectrum) (shared) | 100G (AL2S) (dedicated) | 1 x 100G (spectrum) (Esnet) | 1 x 100G (spectrum) (Esnet) | 1 x 100G ESNET (shared), 1 x 100G Internet2 (shared) | 1 x 100G MREN (shared) | Multiple 100G (shared with DM)
| Notes: | If "(protected)" is not provided, it means that links are LINEAR (not protected)
Statement in Green means under evaluation and is a goal
Purple means it needs further clarification