## Software Development Roadmap
LSST Data Management Software Development Roadmap | [7 empty] | LDM-240 v24
Release | Institution | R4.0 | R5.0/5.1 | R6.0/6.1 | R7.0/7.1 | R8.0/8.1 - #1 Release for ComCam | R9.0/9.1 – #2 Release for ComCam | R10.0/10.1 – LSST Camera
Elapsed time (years) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Finish Date |  | 2014-08-31 | 2015-08-31 | 2016-08-31 | 2017-08-31 | 2018-08-31 | 2019-08-31 | 2020-08-31
Year during which work is done |  | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20
Release Highlights |  | R&D code base mined for reusable components. Stable interfaces for Middleware. Lay foundation for debugging and visualization tools. | Image processing subset of apps framework; Single frame processing pipelines; Pipeline toolkit, simple orchestration and query services | Completion of apps framework; Initial releases of Image Differencing and Coaddition pipelines; Camera SDS interface; Initial Base DMCS for AP, query services user management | PSF Estimation; Deblending; Operation with expected as-built image characteristics; Calibration telescope interface; Initial Archive DMCS for DRP and DAC DMCS | Photometric calibration; Deblending and crowded field support; SUI; Production monitoring, control, and restart | Integrated DMS at LSST-camera commissioning-support level and scale; assembly of all data needed to begin commissioning | Fully integrated DMS at DR1 scale; assembly of all data needed to begin operations
Input Data |  | NA | DES images – first 2 yrs; ImSim delivery 1 (15x15 area, Opsim cadence for 1 yr); Images from LSST SDS test stand | DES images – first 3 yrs; ImSim delivery 2 (delivery 1 plus full equatorial band, two over-the-pole stripes for 1 yr Opsim cadence); Photometric standards catalog | DES images – first 4 yrs; PS-1 detections for MOPS input; PS-1 images if public; Imsim delivery 3 (delivery 2 plus full sky, 1 filter, Opsim cadence for 1 yr) | DES images – full survey; Imsim delivery 4 (delivery 3 + additional year of time coverage, 2 filters) | See commissioning plan | See commissioning plan
Output Data |  | NA | Calibrated Science Images in Image Archive; Metadata and SDQA outputs in database | R5.0 plus Object, Source, DiaSource tables in database; Transient Alerts | R6.0 plus MovingObject table in database; calibrated photometry in Object and Source tables; galaxy shape model parameters in Object table | R7.0 plus astrometric models in Object table | All L1 and L2 data products | All L1 and L2 data products, sample L3 data products
External Interfaces Available |  |  | Camera Phase 3 interface definition | OCS Phase 3 interface definition, simulated images, partial-store Camera SDS testbed | Calibration telescope, OCS command simulator, static EFD. | ComCam, full-capacity EFD simulator. | Full-store SDS testbed. | All external interfaces live
External Interfaces Provided
Integration Tests Enabled
Metrics Measured
02C.01 System Management | LSST
02C.01.02 Science Data Quality Integration and Test | LSST
02C.01.02.01 SDQA Pipeline | LSST |  | R&D code base mined for reusable components. Ability to collect QA data from program outputs and store them into a database. Collect and compute metrics relevant to algorithms in development. | Collect and compute metrics relevant to algorithms in development. | Collect and compute metrics relevant to algorithms in development. | Collect and compute metrics relevant to algorithms in development.
02C.01.02.02 SDQA Toolkit | LSST |  | R&D code base mined for reusable components. Image visualization in support of software development activities. Image and measurement visualization system. (LSE-63 Level 0 DQA) | Image and catalog visualization in support of software development activities Debugging toolkit for LSST software stack. (LSE-63 Level 0 DQA) | Image and catalog visualization in support of software development activities (LSE-63 Level 0 DQA) | Visualization and exploration of telemetry, catalog, and image data in support of nightly observing. (LSE-63 Level 1 DQA) | Visualization and exploration of telemetry, catalog, and image data in support of data release quality analysis. (LSE-63 Level 2 DQA)
02C.01.02.03 Science Pipeline Toolkit | LSST | End-user and developer documentation generated for the DM software stack | LSST DM stack installable and usable by science users | Maintain science user usability of DM stack | Maintain science user usability of DM stack | Maintain science user usability of DM stack | Tools for uploading data to the LSST data center, configuring and running Level 3 pipelines
02C.02 Systems Engineering | LSST
02C.03 Alert Production | University of Washington
02C.03.01 Single Frame Processing Pipelines | University of Washington |  |  | WCS terms needed to describe distortions at edges of chips and near the bloom stop Astrometric registration of a stack of images. Pixel-level intensity-dependent PSF correction Multi-CCD sky background detemination Cross-talk removal Fringe removal | Recognition and retention of trails (moving objects) in visit creation ISR functional with as-built CCD and raft characteristics (based on characterization of sensor/raft prototypes) Measurements functional with as-built CCD and raft characteristics.
02C.03.02 Association Pipeline | University of Washington |  |  |  |  | Association of DIASources to DIAObjects Association of DIAObjects with Objects | Scalability and speed satisfy transient alert latency requirement
02C.03.03 Alert Generation Pipeline | University of Washington | [5 empty] | Transient Alert Packet creation and transmission capability Initial implementation of simple Event Broker | Scalability and speed satisfy transient alert latency requirement Full implementation of simple Event Broker, ability to receive and broker events under expected event and user load.
02C.03.04 Image Differencing Pipeline | University of Washington |  | Overhaul of difference imaging task Research DCR in the context of algorithms and template generation | Difference an image against a deeper template Source detection on difference images using "preconvolution" method. Measurement of PSF Flux and adaptive moments Dipole source fit Quantitative understanding of DCR effects | Detection and masking of artifacts (e.g., bright stars or ghosts) Minimization of artifacts due to imperfect image registration, WCS improvements Trailed source model fit Forced photometry | Spuriousness metric Image differencing with images incorporating as-built sensor characteristics Image differencing of crowded fields DIAObject characterization from DIASources, first release | Selection criteria and strategy for building templates Forced photometry on difference of exposures comprising a visit Integrated deblender Variability characterization. Scalability and speed satisfy alert latency requirement.
02C.03.05 Application Framework for Exposures | University of Washington | AFW R&D code refactored CameraGeometry class redesign. | Redesign and refactor Interpolation and Approximation Aperture corrections | Redesign and refactor Wcs and Coord Development in support of use cases utilizing Exposures | Development in support of use cases utilizing Exposures | Development in support of use cases utilizing Exposures |  |  | ?
02C.03.06 Moving Object Pipelines | University of Washington |  |  |  |  | Fully functional NightMOPS Initial DayMOPS implementation, not parallelized or running at scale | Functional DayMOPS, optimized for slow-moving (non-trailed) asteroids. | Fully functional DayMOPS, including support for linking of trailed objects
02C.03.07 Photometric Self-Calibration Pipelne | University of Washington |  |  |  |  | Set up and solve the least squares system for photometric self calibration (20% DR1 scale) | Solve least squares system for photometric self calibration (full DR1 scale)
02C.03.08 Astrometric Calibration Pipeline | University of Washington |  | Define API and provide minimal implementation of astrometric self-calibration |  |  |  | Set up and solve the least squares system for astrometric calibration (20% DR1 scale) | Solve least squares system for astrometric self calibration (full DR1 scale)
02C.04 Data Release Production | Princeton University
02C.04.01 App Framework for Catalogs | Princeton University | AFW R&D code refactored | Redesign and refactor Footprints | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data |  |  | ?
02C.04.02 Calibration Products Pipeline | Princeton University |  |  | Cross-talk matrix derivation Master bias and dark frame Defect mask construction | Derive illumination correction, pupil ghost, flat field Pipeline for reduction of calibration telescope spectra | Master flat production from monochromatic flats Estimation of telescope-camera bandpasses from monochromatic flats Derivation of atmospheric models. | Fringe frame construction and subtraction Produce initial optical ghost catalog Radiometer and GPS data processing, incorporation in bandpass est. Derive system bandpass given all calibration data Full pipeline functionality
02C.04.03 PSF Estimation | Princeton University |  | Develop interface for full focal plane PSF estimation | Estimation of undersampled PSFs. Estimation of PSFs in the presence of pixel response non-linearity Estimation of Camera-Telescope contribution to PSF from wavefront sensor and Camera metrology | Estimation of PSF variation across the full focal plane (single solution) Improved estimation accuracy and computational performance optimization | PSF estimation at SRD specification level
02C.04.04 Image Coaddition Pipeline | Princeton University |  |  | Build background-matched coadds, PSF and non-PSF matched PSF Flux and Aperture photometry on coadds Measurement using CoaddPSF, initial version | Build chi^2 coadds Coadd source characterization for bootstrapping object characterization | Capability to build coadds in crowded fields Simultaneous generation of multiple coadds | Insertion and recovery of simulated sources
02C.04.05 Deep Detection Pipeline | Princeton University |  |  | Detection of sources on coadds
02C.04.06 Object Characterization Pipeline | Princeton University | Fit models using a greedy optimizer Model-fit galaxy photometry (Sersic models) Morphological star/galaxy separation | Placeholder prototype for multi-band deblender Validation of CModel galaxy colors Performance testing for shape measurement Measurement framework overhaul | Morphological star-galaxy separation Model fitting data in presence of charge-transport effects (distortions near edge and bloom stop) Fit bootstrap using source characterization on coadds Enable decision on final DRP hardware architecture | Multi-coadd deblending and source association Model fitting on images with characteristics of as-built sensors Moving point source object fit, initial version Verification of effectiveness for shape measurement | Improved Multi-coadd deblending and association Model fitting of blended objects Probabilistic star/galaxy separation Computational performance enhancements | Deblender enhancements for crowded fields (crowded field photometry) Creation of sky coverage maps
02C.05 Science User Interface and Analysis Tools | Caltech IPAC
02C.05.01 Basic Archive Access Tools | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | SUI requirement refinement and design. Prototype Web UI Query interface, query image and catalog data using SLAC APIs. Firefly refactoring. | Quick-look previews of query results. Improvements to Query interface, SQL interface, and query specifications for image and catalog data, SUI/database interface. | Browsing of metadata, federation with external catalogs. Improvements to Query interface, query specifications for image and catalog data. | Improvements to Query interface, query specifications for image and catalog data, browsing of metadata, federation with external catalogs. | Improvements to Query interface, query specifications for image and catalog data, browsing of metadata, federation with external catalogs. | Access to Level 3 data products, correlating Level 3 with parent data
02C.05.02 Data Analysis and Visualization Tools | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Prototype 2D plot in web UI, basic scatter XY plot, image display. Prototype the visualization component APIs | Quick-look visualization, image viewer capabilities, overlay capabilities, image cutouts, improvements to interactive catalog/image visualization | Single focal-plane visualization, single-object time-domain view, mosaicking, image coaddition, basic 3D visualization | Survey coverage display, periodograms, track/tracklet/proper motion visualization, image subtraction/blinking | Large-area multi-res image display, advanced light curve visualization, advanced 3D visualization | Light curve fitter, automated template fitter, cross-matching, multi-variable correlation plots, all-sky movie, interactive celestial sphere, 4D visualization
02C.05.03 Alert/Notification Toolkit | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Start to understand the requrements |  |  | Subscription service, object association, predefined filters, user-provided filters, alert history, filtering on alert history | Access to original state of alert, Annotation history, User community discussion forum, API history access | Alert notification mechanisms, viewing annotations, persisting annotations
02C.05.04 User Assistance/Help Desk | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. |  | Create helpdesk, knowledge database, ticketing system, and online documentation access
02C.05.05 User Workspace Toolkit | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Start the definition of workspace | Workspace object upload, download, manipulation, deletion, data object identifiers | Workspace interoperability with SUI/tools, scriptable operation | Improvements to Workspace interoperability with SUI/tools, scriptable operation | Improvements to Workspace interoperability with SUI/tools, scriptable operation | Improvements to Workspace interoperability with SUI/tools, scriptable operation
02C.06 Science Data Archive and Application Services | SLAC
02C.06.01 Science Data Archive | SLAC
02C.06.01.01 Catalogs Alerts and Metadata | SLAC |  | Data ingest scripts for data challenges Initial version of Metadata Service and Database Service | Ongoing improvements Initial versions of Alert Production Catalog and Level 1 DB Catalog | Ongoing improvements Initial versions of Level 2 catalogs Initial version of catalog swap/release automation | Ongoing improvements Initial version of Calibration Database Operations-ready versions of Level 1 catalog and DRP internal catalog. Begin work on Level 3 catalog | Operations-ready versions of all catalogs Bulk download catalog
02C.06.01.02 Image and File Archive | SLAC |  | Provenance of data challenge datasets | Final versions of all functionality
02C.06.02 Data Access Services | SLAC
02C.06.02.01 Data Access Client Framework | SLAC |  | Basic list/put/get butler functionality including database access Limited version of dynamic repository-specific dataset types Initial version of Web Data Access Service Final versions of butler functionality for local datasets | Initial version of provenance Improvements to Web Data Access Service | Improvements to provenance
02C.06.02.02 Data Definition Client Framework | SLAC |  | Final versions of all functionality
02C.06.02.03 Query Services | SLAC |  | Rewrite build and installation scripts and test harness Evaluate alternative systems and components Begin rewrite and restructuring of master, worker, and metadata server Rewrite master and worker and metadata server to support: Creation and removal of distributed databases Creation and loading of prepartitioned distributed tables Initial version of query aborting Implement initial query types Initial prototype of data distribution and replication All of the above robust to user errors, crash-free, and fault-tolerant | Ongoing improvements including more query types Full manipulation of distributed databases and tables Initial user management functionality Improvements to data distribution and replication Initial version of distributed loader Multi-table shared scans Additional loader functionality | Initial version of resource management Ongoing improvements to queries, user management, and loader Fault tolerance demonstration | Ongoing improvements Complete loader functionality Begin working on partial query results. Begin work on Level 3 | Partial query results Initial version of query time estimates, resource management, and Level 3
02C.06.02.04 Image and File Services | SLAC |  | Initial version of image cutout service | Ongoing improvements to image cutout service
02C.07 Processing Control and Site Infrastructure | NCSA
02C.07.01 Processing Control | NCSA
02C.07.01.01 Data Management Control System | NCSA |  | Evaluation of other systems Build prototype AP including events Build prototype production sequence OCS integration | Initial version of AP Initial version of DRP | Improved AP Improved DRP Initial version of DAC DMCS with resource management | Improved AP with full configuration and telemetry Improved DRP Improved DAC | Final AP, DRP Improved DAC | Final DAC
02C.07.01.02 Orchestration Manager | NCSA |  |  | Evaluation of other systems Refactor Orchestration including task deployment and execution | Ongoing improvements Initial version of task control: monitoring and termination | Complete task deployment/execution Complete task control
02C.07.01.03 Pipeline Execution Services | NCSA
02C.07.01.03.01 Pipeline Construction Toolkit | NCSA | Prepare for refactoring |  | Refactor with modifications to support I/O, status tracking, provenance Begin rewrite of configuration | Ongoing improvements Complete configuration rewrite
02C.07.01.03.02 Logging Services | NCSA | Implement basic functionality using off-the-shelf package | Implement advanced functionality including event-based logging
02C.07.01.03.03 Inter-Process Messaging Services | NCSA |  |  | Initial version wrapping MPI and Event Services | Final versions of all functionality
02C.07.01.03.04 Checkpoint/Restart Services | NCSA |  |  | Initial version of pipeline checkpointing (state writing) Initial version of production checkpointing based on Orchestration | Final version of pipeline checkpointing Improved production checkpointing | Final version of production checkpointing
02C.07.02 Infrastructure Services | NCSA
02C.07.02.01 Event Services | NCSA |  | Evaluation of other systems for event monitoring Refactor basic event services | Initial capability for simple event statistics Initial version of event pattern matching | Final version of event matching
02C.07.02.02 Security and Access Control Services | NCSA |  | Developer security |  | Collaborator security | Final versions of all functionality
02C.07.02.03 Dashboard and Performance Visualizations | NCSA |  |  | Understand requirements for and design basic visualization services and Web access |  |  | Full capability, all use cases/activities
02C.07.02.04 System Administration and Operations Services | NCSA |  | OpenStack |  |  | Final versions of all functionality
02C.07.02.05 File System Services | NCSA |  | Processing and evaluation | GPFS |  | Final versions of all functionality
02C.07.02.06 VO Interfaces | NCSA |  |  | TAP v1, ADQL v1, VOEvent v1 | TAP v2, ADQL v2, VOEvent v2 | Final versions of all functionality
02C.07.03 Environment and Tools | NCSA
02C.07.03.01 Software Development Tools (need to split into 02C.07.03 and 02C.01.02 parts) | NCSA | eups, scons, buildbot, distribution server, JIRA, Confluence | github, hipchat
02C.08 International Communications and Base Site | NCSA
02C.09 DM System Integration and Test | LSST

## SW Dev Roadmap - Use Cases
LSST Data Management Software Development Roadmap | [7 empty] | LDM-240 v24
Release | Institution | R4.0 | R5.0/5.1 | R6.0/6.1 | R7.0/7.1 | R8.0/8.1 - #1 Release for ComCam | R9.0/9.1 – #2 Release for ComCam | R10.0/10.1 – LSST Camera
Elapsed time (years) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Finish Date |  | 2014-08-31 | 2015-08-31 | 2016-08-31 | 2017-08-31 | 2018-08-31 | 2019-08-31 | 2020-08-31
Year during which work is done |  | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20
Release Highlights |  | R&D code base mined for reusable components. Stable interfaces for Middleware. Lay foundation for debugging and visualization tools. | Image processing subset of apps framework; Single frame processing pipelines; Pipeline toolkit, simple orchestration and query services | Completion of apps framework; Initial releases of Image Differencing and Coaddition pipelines; Camera SDS interface; Initial Base DMCS for AP, query services user management | PSF Estimation; Deblending; Operation with expected as-built image characteristics; Calibration telescope interface; Initial Archive DMCS for DRP and DAC DMCS | Photometric calibration; Deblending and crowded field support; SUI; Production monitoring, control, and restart | Integrated DMS at LSST-camera commissioning-support level and scale; assembly of all data needed to begin commissioning | Fully integrated DMS at DR1 scale; assembly of all data needed to begin operations
Input Data |  | NA | DES images – first 2 yrs; ImSim delivery 1 (15x15 area, Opsim cadence for 1 yr); Images from LSST SDS test stand | DES images – first 3 yrs; ImSim delivery 2 (delivery 1 plus full equatorial band, two over-the-pole stripes for 1 yr Opsim cadence); Photometric standards catalog | DES images – first 4 yrs; PS-1 detections for MOPS input; PS-1 images if public; Imsim delivery 3 (delivery 2 plus full sky, 1 filter, Opsim cadence for 1 yr) | DES images – full survey; Imsim delivery 4 (delivery 3 + additional year of time coverage, 2 filters) | See commissioning plan | See commissioning plan
Output Data |  | NA | Calibrated Science Images in Image Archive; Metadata and SDQA outputs in database | R5.0 plus Object, Source, DiaSource tables in database; Transient Alerts | R6.0 plus MovingObject table in database; calibrated photometry in Object and Source tables; galaxy shape model parameters in Object table | R7.0 plus astrometric models in Object table | All L1 and L2 data products | All L1 and L2 data products, sample L3 data products
External Interfaces Available |  |  | Camera Phase 3 interface definition | OCS Phase 3 interface definition, simulated images, partial-store Camera SDS testbed | Calibration telescope, OCS command simulator, static EFD. | ComCam, full-capacity EFD simulator. | Full-store SDS testbed. | All external interfaces live
External Interfaces Provided
Integration Tests Enabled
Metrics Measured
02C.01 System Management | LSST
02C.01.02 Science Data Quality Integration and Test | LSST
02C.01.02.01 SDQA Pipeline | LSST | Assess Data Quality for Data Release (v1) | Assess Data Quality for Data Release (v2) | Assess Data Quality for Data Release (v3), Assess Data Quality for Nightly Processing (v1), Assess Data Quality for Nightly Processing at Archive (v1) | Assess Data Quality for Data Release (v4), Assess Data Quality for Nightly Processing (v2), Assess Data Quality for Nightly Processing at Archive (v2), Assess Data Quality for Calibration Products (v1) | Assess Data Quality for Data Release (v5), Assess Data Quality for Nightly Processing (v3), Assess Data Quality for Nightly Processing at Archive (v3), Assess Data Quality for Calibration Products (v2)
02C.01.02.02 SDQA Toolkit | LSST | Display SDQA Metrics (v1), Analyze SDQA Metrics (v1), Correlate SDQA metric with other data (v1), Correlate SDQA metrics (v1) (LSE-63 Level 0 DQA) | Display SDQA Metrics (v2), Analyze SDQA Metrics (v2), Correlate SDQA metric with other data (v2), Correlate SDQA metrics (v2) (LSE-63 Level 0 DQA) | Display SDQA Metrics (v3), Analyze SDQA Metrics (v3), Correlate SDQA metric with other data (v3), Correlate SDQA metrics (v3) (LSE-63 Level 0 DQA) | Display SDQA Metrics (v4), Analyze SDQA Metrics (v4), Correlate SDQA metric with other data (v4), Correlate SDQA metrics (v4) (LSE-63 Level 0 DQA) | Display SDQA Metrics (v5), Analyze SDQA Metrics (v5), Correlate SDQA metric with other data (v5), Correlate SDQA metrics (v5) (LSE-63 Level 1 DQA) | Display SDQA Metrics (v6), Analyze SDQA Metrics (v6), Correlate SDQA metric with other data (v6), Correlate SDQA metrics (v6) (LSE-63 Level 2 DQA)
02C.01.02.03 Science Pipeline Toolkit | LSST | Configure Pipeline Execution (v1), Execute Pipeline (v1), Select Data to be Processed (v1), Select Data to be Stored (v1) | Configure Pipeline Execution (v2), Execute Pipeline (v2), Select Data to be Processed (v2), Select Data to be Stored (v2) | Configure Pipeline Execution (v3), Execute Pipeline (v3), Select Data to be Processed (v3), Select Data to be Stored (v3) | Configure Pipeline Execution (v4), Execute Pipeline (v4), Select Data to be Processed (v4), Select Data to be Stored (v4) | Configure Pipeline Execution (v5), Execute Pipeline (v5), Select Data to be Processed (v5), Select Data to be Stored (v5) Monitor Pipeline Execution (v1), Incorporate User Code into Pipeline (v1), Upload User Codes (v1) | Configure Pipeline Execution (v5), Execute Pipeline (v5), Select Data to be Processed (v5), Select Data to be Stored (v5) Monitor Pipeline Execution (v2), Incorporate User Code into Pipeline (v2), Upload User Codes (v2)
02C.02 Systems Engineering | LSST
02C.03 Alert Production | University of Washington
02C.03.01 Single Frame Processing Pipelines | University of Washington |  | Assemble CCD, Determine Aperture Correction, Determine PSF Remove Instrument Signature (v1) Detect Sources (v1; no binning), Determine Photometric Zeropoint (v1), Measure Single Visit Sources (v1) Determine WCS (v1; multi-CCD) Sum Exposures, Combine Raw Exposures, Remove Exposure Artifacts (v1) Determine Sky Background Model (v1), Calibrate Exposure (v1), Process Raw Exposures to Calibrated Exposure (v1), Perform Single Visit Processing (v1) Perform Deblending and Association (v1) | Detect Sources (v2; with binning); Determine Photometric Zeropoint (v2), Measure Single Visit Sources (v2) Determine WCS (v2; w. edge distortion terms, astrometric registration of image stack) Remove Instrument Signature (v2; pixel-level intensity-dependent PSF correction, cross-talk removal, fringe removal) Determine Sky Background Model (v2; multi-CCD background detemination), Calibrate Exposure (v2), Process Raw Exposures to Calibrated Exposure (v2), Perform Single Visit Processing (v2) | Remove Exposure Artifacts (v3; recognition and retention of trails) Remove Instrument Signature (v3; working with as-built sensors) Measure Single Visit Sources (v3; working with as-built sensors)
02C.03.02 Association Pipeline | University of Washington | Associate with Instance Catalog (v1), Perform DIA Source Association (v1), Perform DIA Object Association (v1), Create Instance Catalog for Visit (v1) |  |  |  | Perform DIA Source Association (v2), Perform DIA Object Association (v2), | Perform DIA Source Association (v2), Perform DIA Object Association (v2),
02C.03.03 Alert Generation Pipeline | University of Washington | [5 empty] | Distribute to Subscribed Users (v1), Distribute to Subscribed Brokers (v1), Generate Alerts (v1), Generate and Distribute Alerts (v1) | Distribute to Subscribed Users (v2), Distribute to Subscribed Brokers (v2), Generate Alerts (v2), Generate and Distribute Alerts (v2)
02C.03.04 Image Differencing Pipeline | University of Washington |  |  | Subtract Calibrated Exposure from Template Exposure (v1), Detect DIA Sources in Difference Exposure (v1; preconvolution), Detect and Characterize DIA Sources (v1), Measure DIA Sources (v1; psfFlux, adaptive moments, dipole) | Subtract Calibrated Exposure from Template Exposure (v2), Detect DIA Sources in Difference Exposure (v2), Detect and Characterize DIA Sources (v2), Measure DIA Sources (v2; trailed source), Identify DIA Sources caused by Artifacts (v1), Perform Difference Image Forced Photometry | Subtract Calibrated Exposure from Template Exposure (v3; crowded fields), Detect DIA Sources in Difference Exposure (v3), Detect and Characterize DIA Sources (v3), Measure DIA Sources (v3; as-built sensors), Identify DIA Sources caused by Artifacts (v2), Estimate Detection Efficiency (v1), Update DIA Object Properties (v1), Calculate DIA Object Flux Variability Metrics (v1), Fit DIA Object Position and Motion (v1) | Subtract Calibrated Exposure from Template Exposure (v4), Detect DIA Sources in Difference Exposure (v4), Detect and Characterize DIA Sources (v4), Measure DIA Sources (v4), Identify DIA Sources caused by Artifacts (v3), Estimate Detection Efficiency (v2) Measure Snap Difference Flux Update DIA Object Properties (v2), Calculate DIA Object Flux Variability Metrics (v2), Fit DIA Object Position and Motion (v2) Perform Precovery Forced Photometry, Perform Difference Image Forced Photometry Process Nightly Observing Run, Prepare for Observing
02C.03.05 Application Framework for Exposures | University of Washington | Low-level Image Operations (v1) Electrical Geometry redesign (Domain Model Object) | Low-level Image Operations (v2) | Low-level Image Operations (v3) | Low-level Image Operations (v4) | Low-level Image Operations (v5) |  |  | ?
02C.03.06 Moving Object Pipelines | University of Washington |  |  |  |  | Create Instance Catalog for Visit (NightMOPS) Process Moving Objects (v1), Link Tracklets into Tracks (v1), Recalculate Solar System Object Properties (v1), Fit Orbit (v1), Find Tracklets (v1) | Process Moving Objects (v2), Link Tracklets into Tracks (v2), Recalculate Solar System Object Properties (v2), Fit Orbit (v2), Find Tracklets (v2); focus on main-belt asteroids Perform Precovery (v1) Prune Moving Object Catalog (v1) | Process Moving Objects (v3), Link Tracklets into Tracks (v3), Recalculate Solar System Object Properties (v3), Fit Orbit (v3), Find Tracklets (v3); focus on fast-moving objects Perform Precovery (v2) Prune Moving Object Catalog (v2)
02C.03.07 Photometric Self-Calibration Pipelne | University of Washington |  |  |  |  | Perform Global Photometric Calibration (v1) | Perform Global Photometric Calibration (v2)
02C.03.08 Astrometric Calibration Pipeline | University of Washington | [5 empty] | Perform Global Astrometric Calibration (v1) | Perform Global Astrometric Calibration (v2)
02C.04 Data Release Production | Princeton University
02C.04.01 App Framework for Catalogs | Princeton University | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data | Development in support of use cases utilizing catalog data |  |  | ?
02C.04.02 Calibration Products Pipeline | Princeton University |  |  | Produce Crosstalk Correction Matrix, Produce Master Bias Exposure, Produce Master Dark Exposure, Construct Defect Map | Determine Optical Model-derived Illumination Correction, Produce Master Pupil Ghost Exposure, Determine Star Raster Photometry-derived Illumination Correction, Determine Illumination Correction (v1), Create Master Illumination Correction (v1), Produce Master Flat-Spectrum Flat Exposures (v1), Correct Monochromatic Flats (v1), Create Master Flat-Spectrum Flat (v1), Produce Calibration Data Products (v1) Reduce Spectrum Exposure | Determine Self-calibration Correction-Derived Illumination Correction, Determine CCOB-derived Illumination Correction, Determine Illumination Correction (v2), Create Master Illumination Correction (v2), Produce Master Flat-Spectrum Flat Exposures (v2), Correct Monochromatic Flats (v2), Create Master Flat-Spectrum Flat (v2), Produce Calibration Data Products (v2), Prepare Nightly Flat Exposures (v1) Calculate Telescope Bandpasses (v1), Calculate System Bandpasses (v1) Calculate Atmospheric Models from Calibration Telescope Spectra (v1) | Produce Master Fringe Exposures, Produce Optical Ghost Catalog, Acquire Raw Calibration Exposures, Determine Illumination Correction (v3), Create Master Illumination Correction (v3), Produce Master Flat-Spectrum Flat Exposures (v3), Correct Monochromatic Flats (v3), Create Master Flat-Spectrum Flat (v3), Produce Calibration Data Products (v3), Prepare Nightly Flat Exposures (v2) Calculate Atmospheric Models from Calibration Telescope Spectra (v2; radiometer & GPS data) Calculate Telescope Bandpasses (v2), Calculate System Bandpasses (v2)
02C.04.03 PSF Estimation | Princeton University |  | Perform Full Focal Plane PSF Estimation (v1) | Perform Full Focal Plane PSF Estimation (v2) | Perform Full Focal Plane PSF Estimation (v3) | Perform Full Focal Plane PSF Estimation (v4), Perform Single Visit Processing
02C.04.04 Image Coaddition Pipeline | Princeton University |  |  | Coadd Calibrated Exposures (v1), Create Deep Coadd Exposures (v1), Create PSF-matched Coadd Exposures (v1), Create Coadd Exposures (v1) | Coadd Calibrated Exposures (v2; quality), Create Deep Coadd Exposures (v2; quality), Create Coadd Exposures (v2; quality), Create PSF-matched Coadd Exposures (v2; quality) Create Template Exposures (v1) | Coadd Calibrated Exposures (v3; performance), Create Deep Coadd Exposures (v3; performance), Create Coadd Exposures (v3; performance), Create PSF-matched Coadd Exposures (v3; performance) Create Template Exposures (v2; performance) Create Short Period Coadd Exposures (v1), Create Best Seeing Coadd Exposures (v1) | Coadd Calibrated Exposures (v4; performance), Create Deep Coadd Exposures (v4; performance), Create Coadd Exposures (v4; performance), Create PSF-matched Coadd Exposures (v4; performance) Create Template Exposures (v3; performance) Create Short Period Coadd Exposures (v2), Create Best Seeing Coadd Exposures (v2)
02C.04.05 Deep Detection Pipeline | Princeton University |  |  | Detect and Characterize AstroObjects, Detect Sources on Coadds
02C.04.06 Object Characterization Pipeline | Princeton University | Measure AstroObjects (v1; greedy optimizer; extended sources; S/G separation) | Measure AstroObjects (v2; MultiFit; performance optimizations) | Measure AstroObjects (v3; StackFit; realistic CCD defects; performance optimizations) Perform Deblending and Association (v2) | Measure AstroObjects (v4; realistic CCDs; moving point source) Perform Deblending and Association (v3) Perform Forced Photometry | Measure AstroObjects (v5; measure blends) Perform Deblending and Association (v4; performance) Characterize AstroObject Flux Variability | Perform Deblending and Association (v5; performance, crowded fields) Create Sky Coverage Maps
02C.05 Science User Interface and Analysis Tools | Caltech IPAC
02C.05.01 Basic Archive Access Tools | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Extract Objects with User-specified Properties Query AstroObject Catalog Query Image Archive | Execute Cone Search Execute Box Search | Federate Query Results with External Catalogs | Extract Time Series for Objects | Extract Time Sequence of Images | Access to Level 3 data products, correlating Level 3 with parent data
02C.05.02 Data Analysis and Visualization Tools | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Create 2D Display of Catalog Query Result Create Histogram Display Exposure Display Light Curve for Objects | Overlay Catalog Query on Image Retrieve Postage Stamp Overlay Cleaned Catalog Query on Image | Create Coadded Exposure Create 3D/4D Display of Catalog Query Result | Display Tracks/Tracklets for Solar System Objects Retrieve Survey Depth Map Subtract One Exposure from Another | Blink/Display Movie of Multiple Images | Calculate Commonly-used Statistics for Catalog Quantities Generate and Display Periodogram for AstroObjects
02C.05.03 Alert/Notification Toolkit | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. |  |  |  | Create Alert Category Create an Alert Filter Process Subscription Requests Record Alert Retrieve Alerts Subscribe to Alert Category | Access to original state of alert, Annotation history, User community discussion forum, API history access | Deliver Alerts
02C.05.04 User Assistance/Help Desk | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. | Help Desk with Query Tracking
02C.05.05 User Workspace Toolkit | Caltech IPAC | Evaluate best-of-breed tools. Technology exploration. |  | Save Query Result to User Workspace | Workspace interoperability with SUI/tools (v1), scriptable operation | Workspace interoperability with SUI/tools (v2) | Workspace interoperability with SUI/tools (v3) | Workspace interoperability with SUI/tools (v4)
02C.06 Science Data Archive and Application Services | SLAC
02C.06.01 Science Data Archive | SLAC
02C.06.01.01 Catalogs Alerts and Metadata | SLAC | Ingest Image Metadata Beta, Ingest FITS Table Beta, Ingest Multiple FITS Tables Beta, Ingest Production Results Beta | Construct Global Catalog v1, Ingest Image Metadata, Ingest FITS Table, Ingest Multiple FITS Tables, Ingest Production Results | Construct Global Catalog v2, Construct Temporary Alert Production Catalog v1, Construct Level 1 Database Catalog v1 | Construct Global Catalog v3, Construct Temporary Alert Production Catalog v2, Construct Level 1 Database Catalog v2, Construct Temporary Data Release Production Catalog Beta, Construct Data Release Catalog v1, Release New Catalog v1 | Construct Global Catalog v4, Construct Temporary Alert Production Catalog, Construct Level 1 Database Catalog, Construct Temporary Data Release Production Catalog, Construct Data Release Catalog v2, Release New Catalog v2 | Construct Global Catalog, Construct Data Release Catalog, Release New Catalog, Bulk Download Catalog
02C.06.01.02 Image and File Archive | SLAC |  | List Released Images and Files Beta, Retrieve Released Image or File Beta, Bulk Download Images and Files Beta | List Released Images and Files, Retrieve Released Image or File, Bulk Download Images and Files
02C.06.02 Data Access Services | SLAC
02C.06.02.01 Data Access Client Framework | SLAC | Create Repository Beta, Add Dataset Type Beta, List Dataset Types, List Data Identifier Keys, Add Dataset, Retrieve Dataset, Retrieve Dataset Provenance Beta, List Datasets | Create Repository, Add Dataset Type, Retrieve Dataset Provenance, Verify Dataset Signature, Remove Dataset | Retrieve Remote Dataset
02C.06.02.02 Data Definition Client Framework | SLAC | Define Schema, Create Table
02C.06.02.03 Query Services | SLAC |  | Administration v1, Create Database Beta, Drop Database Beta, Create Distributed Table Beta, Load Tables v1, Remove Table Beta, Submit SQL-Like Query v1, Recognize Spatial SQL Extensions Beta, Recognize Common Non-SQL92 Syntax v1, Recognize and Execute Simple Queries Beta, Recognize and Execute Scan Queries v1, Recognize and Execute Shared Scan Queries v1, Abort Query Beta | Administration v2, Database User Management v1, Create Database, Drop Database, Create Distributed Table, Load Tables v2, Remove Table, Submit SQL-Like Query v2, Recognize Spatial SQL Extensions, Recognize Common Non-SQL92 Syntax v2, Recognize and Execute Simple Queries, Recognize and Execute Scan Queries v2, Recognize and Execute Shared Scan Queries v2, Abort Query | Administration v3, Database User Management v2, Load Tables v3, Submit SQL-Like Query v3, Recognize Common Non-SQL92 Syntax v3, Recognize and Execute Scan Queries v3, Recognize and Execute Shared Scan Queries v3 | Administration v4, Database User Management v3, Load Tables, Submit SQL-Like Query v4, Recognize Common Non-SQL92 Syntax v3, Recognize and Execute Scan Queries v4, Recognize and Execute Shared Scan Queries v4 | Administration v5, Database User Management, Submit SQL-Like Query v5, Recognize Common Non-SQL92 Syntax, Recognize and Execute Scan Queries, Recognize and Execute Shared Scan Queries v5, Return Partial Query Result, Estimate Time for Query v1, Resource Management v1, Level 3 Queries v1 | Administration v6, Submit SQL-Like Query v6, Recognize and Execute Shared Scan Queries, Estimate Time for Query v2, Resource Management v2, Level 3 Queries v2
02C.06.02.04 Image and File Services | SLAC |  | Regenerate FITS File Beta | Regenerate FITS File, Retrieve Calibrated Science Image, Retrieve Difference Image, Retrieve Image Mosaic, Retrieve RGB Image, Retrieve Cutout Image
02C.07 Processing Control and Site Infrastructure | NCSA
02C.07.01 Processing Control | NCSA
02C.07.01.01 Data Management Control System | NCSA |  |  | init Beta, configure v1, Archiver, Catch-Up Archiver v1, Alert Production Cluster, EFD Replicator beta, OCS Interface, startIntegration v1, Archive Image v1, nextVisit v1, Manage Production Phase Execution v1 | init, configure v2, Catch-Up Archiver v2, EFD Replicator, startIntegration v2, Archive Image v2, nextVisit v2, Manage Production Phase Execution v2, Resource Management v1 | configure, Catch-Up Archiver, startIntegration v3, Archive Image v3, nextVisit v3, Manage Production Phase Execution v3, Resource Management v2 | startIntegration, Archive Image, nextVisit, Manage Production Phase Execution, Resource Management v3 | Resource Management v4
02C.07.01.02 Orchestration Manager | NCSA |  | Define Platform v1, Deploy and Execute Task/Graph on Platform v1, Define Execution Environment Beta, Configure Access to Data v1, Record Task Execution Status Beta | Define Platform v2, Deploy and Execute Task/Graph on Platform v2, Define Execution Environment, Configure Access to Data v2, Record Task Execution Status, Monitor Task Execution v1, Terminate Task Execution v1 | Define Platform v3, Deploy and Execute Task/Graph on Platform, Configure Access to Data, Monitor Task Execution v2, Terminate Task Execution v2 | Define Platform v4, Monitor Task Execution, Terminate Task Execution | Define Platform
02C.07.01.03 Pipeline Execution Services | NCSA
02C.07.01.03.01 Pipeline Construction Toolkit | NCSA | Redesign including Camera team input | Define Task Configuration Beta, Define Task Inputs and Outputs v1, Define Task Arguments, Set Task Metadata Item, Override Task Configuration from File, Override Task Configuration from Arguments, Validate Task Configuration, Freeze Task Configuration, Print Task Configuration Documentation, Print Task Configuration History, Persist Task Configuration, Execute Task Serially, Execute Task in Parallel on One Machine | Define Task Configuration, Define Task Inputs and Outputs v2 | Define Task Inputs and Outputs
02C.07.01.03.02 Logging Services | NCSA | Create Log Object, Define Common Log Metadata Beta, Create Log Entry Beta, Define Log Destination, Define Log Message Format Beta, Configure Logging Services Beta | Define Common Log Metadata, Create Log Entry, Define Log Message Format, Configure Logging Services
02C.07.01.03.03 Inter-Process Messaging Services | NCSA |  | Initialize Inter-Process Task Beta, Define Communications Geometry Beta, Send Data Item(s) Beta, Receive Data Item(s) Beta | Initialize Inter-Process Task, Define Communications Geometry, Send Data Item(s), Receive Data Item(s
02C.07.01.03.04 Checkpoint/Restart Services | NCSA |  |  | Pipeline Checkpoint Beta, Production Checkpoint v1 | Pipeline Checkpoint, Production Checkpoint v2 | Define Production Checkpoint, Restart Production from Checkpoint
02C.07.02 Infrastructure Services | NCSA
02C.07.02.01 Event Services | NCSA |  | Basic Event Services, Configure Event Monitor v1, Process Incoming Event v1, Maintain Event Statistics, Recognize Event, Recognize Missing Event Beta, Recognize Event Pattern v1 | Configure Event Monitor v2, Process Incoming Event v2, Recognize Missing Event, Recognize Event Pattern v1 | Configure Event Monitor, Process Incoming Event, Recognize Event Pattern
02C.07.02.02 Security and Access Control Services | NCSA | Developer security |  |  | Collaborator security | Full capability, all use cases/activities
02C.07.02.03 User Interface/Visualization Services | NCSA | Understand requirements for and design basic visualization services and Web access |  |  |  |  | Full capability, all use cases/activities
02C.07.02.04 System Administration and Operations Services | NCSA |  |  |  |  | Full capability, all use cases/activities
02C.07.02.05 File System Services | NCSA |  |  | GPFS |  | Full capability, all use cases/activities
02C.07.02.06 VO Interfaces | NCSA |  |  | TAP v1, ADQL v1, VOEvent v1 | TAP v2, ADQL v2, VOEvent v2 | Full capability, all use cases/activities
02C.07.03 Environment and Tools | NCSA
02C.07.03.01 Software Development Tools | NCSA | github/Stash, eups, scons, buildbot, distribution server, JIRA, Confluence
02C.08 International Communications and Base Site | NCSA
02C.09 DM System Integration and Test | LSST

## Key Performance Metrics
LSST Data Management Key Performance Metrics | [12 empty] | LDM-240 v24
Release | Unit | Contributing Elements | R4.0 | R5.0/5.1 | R6.0/6.1 | R7.0/7.1 | R8.0/8.1 - #1 Release for ComCam | R9.0/9.1 – #2 Release for ComCam | R10.0/10.1 – LSST Camera | Operational Readiness | Guiding Requirement
Elapsed time (years) |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Finish Date |  |  | 2014-08-31 | 2015-08-31 | 2016-08-31 | 2017-08-31 | 2018-08-31 | 2019-08-31 | 2020-08-31 |  | Design | Minimum (SRD) | Source
Year during which work is done |  |  | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20
Photometric repeatability
procCalRep | mmag | SFM | 15 | 13 | 10 | 5 | 5 | 4 | 3.5 | 3 | 3 |  | OSS-REQ-0275
PA1gri | mmag | SFM, CPP, PhotoCal | 15 | 13 | 12 | 8 | 8 | 6 | 5.5 | 5 | 5 | 8 | LSR-REQ-0093
PA1uzy | mmag | SFM, CPP, PhotoCal | 15 | 13 | 14 | 12 | 12 | 8 | 8 | 7.5 | 7.5 | 12 | LSR-REQ-0093
Photometric Spatial Uniformity
PA3u | mmag | PhotoCal |  |  |  |  | 40 | 30 | 20 | 20 | 20 | 30 | LSR-REQ-0093
PA3 (g) | mmag | PhotoCal |  |  |  |  | 30 | 15 | 10 | 10 | 10 | 15 | LSR-REQ-0093
PA3 (y) | mmag | PhotoCal |  |  |  |  | 30 | 15 | 10 | 10 | 10 | 15 | LSR-REQ-0093
Color Zero-point Accuracy
PA5 | mmag | PhotoCal |  |  |  |  | 30 | 20 | 10 | 5 | 5 | 10 | LSR-REQ-0093
PA5u | mmag | PhotoCal |  |  |  |  | 50 | 30 | 15 | 10 | 10 | 15 | LSR-REQ-0093
Absolute Photometry Accuracy
PA6 | mas | PhotoCal | [5 empty] | 30 | 20 | 10 | 10 | 20 | LSR-REQ-0093
Relative Astrometry
AM1 | mas | SFM, ObjChar | 80 | 60 | 50 | 30 | 30 | 20 | 15 | 10 | 10 | 20 | LSR-REQ-0094
AM2 | mas | SFM, ObjChar | 80 | 60 | 50 | 30 | 30 | 20 | 15 | 10 | 10 | 20 | LSR-REQ-0094
AM3 | mas | SFM, ObjChar, AstroCal | 100 | 75 | 50 | 40 | 40 | 30 | 20 | 15 | 15 | 30 | LSR-REQ-0094
AB1 | mas | SFM, ObjChar, AstroCal |  |  |  | 30 | 30 | 20 | 15 | 10 | 10 | 20 | LSR-REQ-0094
Absolute Astrometry
AA1 | mas | AstroCal | [5 empty] | 100 | 75 | 50 | 50 | 100 | LSR-REQ-0094
Residual PSF Ellipticity Correlations
TE1 | - | PsfEst, ObjChar, Coadd |  | 0.005 | 0.001 | 0.0001 | 3e-05 | 3e-05 | 2e-05 | 2e-05 | 2e-05 | 3e-05 | LSR-REQ-0097
TE2 | - | PsfEst, ObjChar, Coadd |  | 0.005 | 0.001 | 1e-05 | 3e-07 | 3e-07 | 2e-07 | 1e-07 | 1e-07 | 3e-07 | LSR-REQ-0097
Moving Object Linkage Efficiency
orbitCompleteness | % | MOPS |  |  |  | 75 | 85 | 90 | 95 |  | 95 |  | OSS-REQ-0159
Spuriousness Metric Efficiency
transCompletenessMin | % | Diffim |  |  |  |  | 50 | 70 | 80 | 90 | 90 |  | OSS-REQ-0353
transPurityMin | % | Diffim |  |  |  |  | 80 | 85 | 90 | 95 | 95 |  | OSS-REQ-0353
mopsCompletenessMin | % | Diffim |  |  |  |  | 75 | 85 | 95 | 99 | 99 |  | OSS-REQ-0354
mopsPurityMin | % | Diffim |  |  |  |  | 25 | 40 | 45 | 50 | 50 |  | OSS-REQ-0354
Computational Performance Metrics
OTT1 | seconds | All AP Pipelines + MW + Infra |  | 240 | 240 | 240 | 180 | 120 | 90 | 60 | 60 | 120
AP computational budget | TFLOPS | All AP Pipelines + MW |  | 231.06 | 192.55 | 154.04 | 77.02 | 57.765 | 57.765 | 38.51 | 38.51 |  | LDM-138¦Output¦C4
DRP computational budget (DR1) | TFLOPS | All DRP+AP Pipelines |  | 645.18 | 215.06 | 161.295 | 150.542 | 129.036 | 107.53 | 107.53 | 107.53 |  | LDM-138¦Output¦F4
LV query rate | simult. queries | qserv |  | 50 | 50 | 50 | 70 | 80 | 100 | 100 | 100 |  | LSE-81¦G263
LV query response time | seconds | qserv |  | 18 | 15 | 12 | 12 | 12 | 10 | 10 | 10 |  | LSE-81¦G270
HV shared scan duration | hours | qserv |  | 24 | 24 | 20 | 18 | 14 | 12 | 12 | 12 |  | LSE-81¦G283
HV simultaneous queries | queries | qserv |  | 6 | 6 | 6 | 8 | 10 | 12 | 12 | 12 |  | LSE-81¦G284
System Reliability Metrics
sciVisitAlertDelay | % | All AP Pipelines | [5 empty] | 10 | 5 | 1 | 1 |  | OSS-REQ-0112
sciVisitAlertFailure | % | All AP Pipelines | [5 empty] | 2 | 0.5 | 0.1 | 0.1 |  | OSS-REQ-0112
sciImageLoss | % | Image and File Archive | [5 empty] | 2 | 1 | 1 | 1 |  | OSS-REQ-0111

## Dependencies (transposed)
LSST Data Management Software Development Roadmap | [6 empty] | LDM-240 v24
Release | R4.0 | R5.0/5.1 | R6.0/6.1 | R7.0/7.1 | R8.0/8.1 - #1 Release for ComCam | R9.0/9.1 – #2 Release for ComCam | R10.0/10.1 – LSST Camera
Elapsed time (years) | 1 | 2 | 3 | 4 | 5 | 6 | 7
Finish Date | 2014-08-31 | 2015-08-31 | 2016-08-31 | 2017-08-31 | 2018-08-31 | 2019-08-31 | 2020-08-31
Year during which work is done | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20
02C.01 System Management
02C.01.02 Science Data Quality Integration and Test
02C.01.02.01 SDQA Pipeline | 02C.06.01.01 Catalogs Alerts and Metadata R4 FF 02C.06.02.01 Data Access Client Framework R4 FF 02C.07.01.03.02 Logging Services R4 FF | 02C.03.02 Association Pipeline R4 FS
02C.01.02.02 SDQA Toolkit |  | 02C.01.02.01 SDQA Pipeline R5 FF 02C.03.02 Association Pipeline R4 FS | 02C.01.02.01 SDQA Pipeline R6 FF | 02C.01.02.01 SDQA Pipeline R7 FF | 02C.01.02.01 SDQA Pipeline R8 FF
02C.01.02.03 Science Pipeline Toolkit
02C.02 Systems Engineering
02C.03 Alert Production
02C.03.01 Single Frame Processing Pipelines |  | 02C.03.02 Association Pipeline R4 FS 02C.06.02.01 Data Access Client Framework R4 FS
02C.03.02 Association Pipeline
02C.03.03 Alert Generation Pipeline | [5 empty] | 02C.03.04 Image Differencing Pipeline R8 FS
02C.03.04 Image Differencing Pipeline |  |  | 02C.03.01 Single Frame Processing Pipelines R5 FS 02C.03.05 Application Framework for Exposures R5 FS | 02C.03.01 Single Frame Processing Pipelines R6 FS | 02C.03.01 Single Frame Processing Pipelines R7 FS 02C.03.02 Association Pipeline R8 FF | 02C.04.02 Calibration Products Pipeline R9 FF
02C.03.05 Application Framework for Exposures |  | 02C.06.02.01 Data Access Client Framework R4 FS 02C.06.02.02 Data Definition Client Framework R4 FS 02C.07.01.03.01 Pipeline Construction Toolkit R4 FS 02C.07.01.03.02 Logging Services R4 FS
02C.03.06 Moving Object Pipelines |  |  |  |  | 02C.03.04 Image Differencing Pipeline R6 FS
02C.03.07 Photometric Self-Calibration Pipelne |  |  |  |  | 02C.03.01 Single Frame Processing Pipelines R5 FS | 02C.04.02 Calibration Products Pipeline R8 FS
02C.03.08 Astrometric Calibration Pipeline | [5 empty] | 02C.03.01 Single Frame Processing Pipelines R6 FS
02C.04 Data Release Production
02C.04.01 App Framework for Catalogs |  | 02C.06.02.01 Data Access Client Framework R4 FS 02C.06.02.02 Data Definition Client Framework R4 FS 02C.07.01.03.01 Pipeline Construction Toolkit R4 FS 02C.07.01.03.02 Logging Services R4 FS
02C.04.02 Calibration Products Pipeline
02C.04.03 PSF Estimation |  | 02C.01.02.01 SDQA Pipeline R4 FS 02C.01.02.02 SDQA Toolkit R4 FS 02C.03.05 Application Framework for Exposures R4 FS 02C.04.05 Deep Detection Pipeline R4 FS | 02C.06.03.03 Inter-Process Messaging Services R6 FF
02C.04.04 Image Coaddition Pipeline |  |  | 02C.04.03 PSF Estimation R5 FS | 02C.03.01 Single Frame Processing Pipelines R6 FS | 02C.03.01 Single Frame Processing Pipelines R7 FS 02C.04.03 PSF Estimation R6 FS 02C.07.01.03.03 Inter-Process Messaging Services R6 FS
02C.04.05 Deep Detection Pipeline |  |  | 02C.04.04 Image Coaddition Pipeline R6 FF
02C.04.06 Object Characterization Pipeline |  | 02C.03.05 Application Framework for Exposures R5 FF | 02C.04.04 Image Coaddition Pipeline R6 FF 02C.04.05 Deep Detection Pipeline R6 FF |  |  | 02C.03.04 Image Differencing Pipeline R9 FF 02C.04.02 Calibration Products Pipeline R9 FF
02C.05 Science User Interface and Analysis Tools
02C.05.01 Basic Archive Access Tools |  | 02C.06.02 Data access service APIs R5 FF
02C.05.02 Data Analysis and Visualization Tools |  | 02C.06.02 Data access service APIs R5 FF
02C.05.03 Alert/Notification Toolkit
02C.05.04 User Assistance/Help Desk
02C.05.05 User Workspace Toolkit
02C.06 Science Data Archive and Application Services
02C.06.01 Science Data Archive
02C.06.01.01 Catalogs Alerts and Metadata
02C.06.01.02 Image and File Archive
02C.06.02 Data Access Services
02C.06.02.01 Data Access Client Framework
02C.06.02.02 Data Definition Client Framework
02C.06.02.03 Query Services
02C.06.02.04 Image and File Services
02C.07 Processing Control and Site Infrastructure
02C.07.01 Processing Control
02C.07.01.01 Data Management Control System
02C.07.01.02 Orchestration Manager
02C.07.01.03 Pipeline Execution Services
02C.07.01.03.01 Pipeline Construction Toolkit
02C.07.01.03.02 Logging Services
02C.07.01.03.03 Inter-Process Messaging Services
02C.07.01.03.04 Checkpoint/Restart Services
02C.07.02 Infrastructure Services
02C.07.02.01 Event Services
02C.07.02.02 Security and Access Control Services
02C.07.02.03 User Interface/Visualization Services
02C.07.02.04 System Administration and Operations Services
02C.07.02.05 File System Services
02C.07.02.06 VO Interfaces
02C.07.03 Environment and Tools
02C.07.03.01 Software Development Tools
02C.07.03.04 Pre-Cursor and Simulated Data Server
02C.07.03.06 Test Data
02C.07.03.07 Test Harnesses and Scripts
02C.07.03.08 Operational Control and Monitoring System
02C.08 International Communications and Base Site
02C.09 DM System Integration and Test

## Change History
Date of TCT approval or editing | TCT approved? | Internal version # | Description of Changes
2013-10-10 |  |  | Initial change-controlled version
2013-10-14 |  |  | Incorporate the Key Performance Metrics sheet
2014-04-21 |  | v20 | Incorporated changes to Calibration and Pipeline Execution assignments to institutions
2015-02-11 |  | v22 | Corrected WBS headings. Transposed dependencies to "depends on" form. (gpdf)
2015-03-02 |  | v23 | Cleaned up some leftovers of past WBS reorganizations on the "Use Cases" sheet. Improved some Excel technicalities. Prepare for merging of FY15 updates from CAMs. (gpdf)
2015-03-10 |  | v24 | FY15 inputs received from all CAMs. 02C.07.02.03, "Dashboard and Performance Visualizations" renamed. Some corrections to dependencies in R4. NB: no updates to Use Case or KPM tabs. Old (untransposed) Dependencies tab deleted. (gpdf)